## Sprint 1
Story name | Story Value | Task Value | Task Description | Thu | Fri | Sat | Sun | Mon | Tue | Task | Thu | Fri | Sat | Sun | Mon | Tue
Story 1 | 5 | 1 | [Story 1] add basic instruction for the user #28 | 0 | 1 | 0 | 0 | 0 | 0 | Task 1 | 0 | 1 | 0 | 0 | 0 | 0
|  | 2 | [Story 1] set up the website framework #29 | 1 | 0 | 0 | 0 | 0 | 0 | Task 2 | 2 | 0 | 0 | 0 | 0 | 0
|  | 2 | [Story 1] add website title and basic formatting #27 | 0 | 1 | 0 | 0 | 0 | 0 | Task 3 | 0 | 2 | 0 | 0 | 0 | 0
Story 2 | 5 | 3 | [Story 2] add search bar / dropdown boxes for country selection #24 | 0 | 0 | 1 | 0 | 0 | 0 | Task 4 | 0 | 0 | 3 | 0 | 0 | 0
|  | 2 | [Story 2] User sees data for country pertaining to 3 restrictions #21 | 0 | 0 | 0 | 1 | 0 | 0 | Task 5 | 0 | 0 | 0 | 2 | 0 | 0
Story 3 | 13 | 8 | [Story 3] Redo map code to take Json input. #48 | 0 | 0 | 0 | 0 | 0 | 1 | Task 6 | 0 | 0 | 0 | 0 | 0 | 8
|  | 5 | [Story 3] Explore github to find ideas we can use for map #44 | 0 | 0 | 0 | 0 | 1 | 0 | Task 7 | 0 | 0 | 0 | 0 | 5 | 0
Story 4 | 3 | 3 | [Story 4] Get from output of search to display of values/ text on the website #45 | 0 | 0 | 0 | 0 | 1 | 0 | Task 8 | 0 | 0 | 0 | 0 | 3 | 0
Story 5 | 8 | 8 | [Story 5] add if then statement to translate quarantineInfo, publicTransportInfo, and facialCoveringsInfo into the three boxes #46 | 0 | 0 | 0 | 0 | 1 | 0 | Task 9 | 0 | 0 | 0 | 0 | 8 | 0

## Sprint 2
Story name | Story Value | Task Value | Task Description | Thu | Fri | Sat | Sun | Mon | Task | Thu | Fri | Sat | Sun
Story 6 | 8 | 3 | [Story 6] Create new machine-readable format file (probably CSV) for making this map #99 | 0 | 1 | 0 | 0 |  | Task 1 | 0 | 3 | 0 | 0
|  | 2 | [Story 6] Use Oxford data to differentiate between different entry restriction levels (C8: 0/ 1 vs. 2, vs. 3/4) and represent on page #100 | 0 | 1 | 0 | 0 |  | Task 2 | 0 | 2 | 0 | 0
|  | 3 | [Story 6] Replace current map ("Government Stringency Index") with a "Where Can I Travel To?" title map #98 | 0 | 1 | 0 | 0 |  | Task 3 | 0 | 3 | 0 | 0
story 7 | 13 | 2 | [Story 7] Clean up pages with CSS (About Us) #80 | 0 | 0 | 1 | 0 |  | Task 4 | 0 | 0 | 2 | 0
|  | 1 | [Story 7] Crop our photos / make them circular #82 | 0 | 1 | 0 | 0 |  | Task 5 | 0 | 1 | 0 | 0
|  | 1 | [Story 7] Add role information (e.g., scrum master, product manager) #81 | 0 | 0 | 1 | 0 |  | Task 6 | 0 | 0 | 1 | 0
|  | 1 | [Story 7] Add more about interests / backgrounds #83 | 0 | 0 | 0 | 1 |  | Task 7 | 0 | 0 | 0 | 1
|  | 2 | On main page, ensure consistent element formatting (sections/divs/etc.) #112 | 0 | 0 | 0 | 1 |  | Task 8 | 0 | 0 | 0 | 2
|  | 2 | Fix search bar overlapping with text issue (right now is fixed location on the page) #111 | 0 | 0 | 1 | 0 |  | Task 9 | 0 | 0 | 2 | 0
|  | 4 | Fix wrapping issue (across browser sizes if possible) on homepage - optimize for web #110 | 0 | 0 | 0 | 1 |  | Task 10 | 0 | 0 | 0 | 4
story 8 | 3 | 1 | [Story8]Link to countries' public health resources #90 | 0 | 1 | 0 | 0 |  | Task 11 | 0 | 1 | 0 | 0
|  | 1 | [Story8] Add text disclaimer #84 | 0 | 1 | 0 | 0 |  | Task 12 | 0 | 1 | 0 | 0
|  | 1 | [Story8]Revise descriptions generated by certain inputs to make sure people are aware of how they need to behave #89 | 0 | 0 | 1 | 0 |  | Task 13 | 0 | 0 | 1 | 0
story 10 | 13 | 1 | [Story 10] Update background for "warmer tones" (i.e., a lighter color instead of dark blue) #95 | 1 | 0 | 0 | 0 |  | Task 14 | 1 | 0 | 0 | 0
|  | 2 | [Story 10] Move the numbers/ values on left-side of main page to be on top text explainers (Oxford values) #96 | 0 | 1 | 0 | 0 |  | Task 15 | 0 | 2 | 0 | 0
|  | 2 | [Story 10] Write-up that "exact match" requirement for search (i.e., capitalization) above search bar #92 | 1 | 0 | 0 | 0 |  | Task 16 | 2 | 0 | 0 | 0
|  | 2 | [Story 10] Link for more information about these numbers visit the 'About This Page' near the Oxford values #97 | 0 | 0 | 1 | 0 |  | Task 17 | 0 | 0 | 2 | 0
|  | 3 | [Story 10] Make date more intuitive (i.e., in "data current as of [date]) instead of its current format #94 | 0 | 0 | 0 | 1 |  | Task 18 | 0 | 0 | 0 | 3
|  | 3 | [Story 10] Create Html tables to house restriction output on the main page (mask wearing ) | 0 | 0 | 1 | 0 |  | Task 19 | 0 | 0 | 3 | 0
story 11 | 8 | 1 | [Story 11] All team members do a final review and sign off before submitting final project #85 | 0 | 0 | 0 | 1 |  | Task 20 | 0 | 0 | 0 | 1
|  | 3 | [Story 11] Modify the Search Bar (full width) #86 | 0 | 0 | 1 | 0 |  | Task 21 | 0 | 0 | 3 | 0
|  | 4 | [Story 11] Polish User Stories, Definitions of Done/ Projects, and make sure Issues are linked to Backog (Github) #88 | 0 | 0 | 0 | 1 |  | Task 22 | 0 | 0 | 0 | 4

## Sprint 1 & 2
Story name | Story Value | Task Value | Task Description | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Task | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
Story 1 | 5 | 1 | [Story 1] add basic instruction for the user #28 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Task 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 | [Story 1] set up the website framework #29 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Task 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 | [Story 1] add website title and basic formatting #27 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Task 3 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Story 2 | 5 | 3 | [Story 2] add search bar / dropdown boxes for country selection #24 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Task 4 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 | [Story 2] User sees data for country pertaining to 3 restrictions #21 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Task 5 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Story 3 | 13 | 8 | [Story 3] Redo map code to take Json input. #48 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Task 6 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0
|  | 5 | [Story 3] Explore github to find ideas we can use for map #44 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Task 7 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Story 4 | 3 | 3 | [Story 4] Get from output of search to display of values/ text on the website #45 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Task 8 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0
Story 5 | 8 | 8 | [Story 5] add if then statement to translate quarantineInfo, publicTransportInfo, and facialCoveringsInfo into the three boxes #46 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Task 9 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0
Story 6 | 8 | 3 | [Story 6] Create new machine-readable format file (probably CSV) for making this map #99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Task 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0
|  | 2 | [Story 6] Use Oxford data to differentiate between different entry restriction levels (C8: 0/ 1 vs. 2, vs. 3/4) and represent on page #100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Task 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
|  | 3 | [Story 6] Replace current map ("Government Stringency Index") with a "Where Can I Travel To?" title map #98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Task 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0
story 7 | 13 | 2 | [Story 7] Clean up pages with CSS (About Us) #80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Task 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
|  | 1 | [Story 7] Crop our photos / make them circular #82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Task 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
|  | 1 | [Story 7] Add role information (e.g., scrum master, product manager) #81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Task 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
|  | 1 | [Story 7] Add more about interests / backgrounds #83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Task 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | 2 | On main page, ensure consistent element formatting (sections/divs/etc.) #112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Task 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
|  | 2 | Fix search bar overlapping with text issue (right now is fixed location on the page) #111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Task 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
|  | 4 | Fix wrapping issue (across browser sizes if possible) on homepage - optimize for web #110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Task 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
story 8 | 3 | 1 | [Story8]Link to countries' public health resources #90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Task 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
|  | 1 | [Story8] Add text disclaimer #84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Task 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
|  | 1 | [Story8]Revise descriptions generated by certain inputs to make sure people are aware of how they need to behave #89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Task 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
story 10 | 13 | 1 | [Story 10] Update background for "warmer tones" (i.e., a lighter color instead of dark blue) #95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Task 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
|  | 2 | [Story 10] Move the numbers/ values on left-side of main page to be on top text explainers (Oxford values) #96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Task 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
|  | 2 | [Story 10] Write-up that "exact match" requirement for search (i.e., capitalization) above search bar #92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Task 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
|  | 2 | [Story 10] Link for more information about these numbers visit the 'About This Page' near the Oxford values #97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Task 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
|  | 3 | [Story 10] Make date more intuitive (i.e., in "data current as of [date]) instead of its current format #94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Task 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
|  | 3 | [Story 10] Create Html tables to house restriction output on the main page (mask wearing ) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Task 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
story 11 | 8 | 1 | [Story 11] All team members do a final review and sign off before submitting final project #85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Task 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | 3 | [Story 11] Modify the Search Bar (full width) #86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Task 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
|  | 4 | [Story 11] Polish User Stories, Definitions of Done/ Projects, and make sure Issues are linked to Backog (Github) #88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Task 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4